## Change Log
Change Log · Sample Project · updated 2026-09-15
变更序号 | 采购包名称 | 供应商 | 变更内容 | 详细说明 | 预估金额 | 最终确认金额 | 时间影响 | 当前状态 | COD已发出 | PMI已发出 | 技术文件提交 | 技术审核中 | 技术确认 | 商务确认 | 商务金额确认 | Change PO下发 | 已取消 | 归档路径 | 备注
COD076 | GC works | Infinity | GC work to accommodate additional network ports in HWT battery | According to HWT battery’s latest requirement update, some IT ports need to be added in the labs and office area. Therefore, GC needs to provide conduits and related site corporation to proceed this change. | ¥20,000.00 |  | No schedule impact | PMI 已发出 | 2026-07-13T14:17:16+08:00 | 2026-07-13T14:45:17+08:00 | [7 empty] | 01_GC_works_Infinity/04_变更洽商/
COT003 | Glazing partition | Facade Co | 增加一道防火门 | 门洞两侧补强、防火门及五金按最新消防图纸施工；不含门禁与弱电部分。 | ¥15,000.00 | ¥16,800.00 |  | Change PO 下发 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 | 2026-08-08T22:00:00+08:00 |  | 01_Glazingpartition_Facade/04_变更洽商/ | 金额来源邮件；不含税
COT007 | BMS | CtrlSys | 加点位取消方案回退 | 原 COD 要求增加若干点位；业主决定维持原设计，本变更取消。 | ¥8,000.00 |  |  | 已取消 | 2026-08-10T10:00:00+08:00 | 2026-08-11T09:30:00+08:00 | [6 empty] | 2026-08-15T16:00:00+08:00 | 01_BMS_CtrlSys/04_变更洽商/ | 手改取消；之后邮件只归档不推进
COT012 | IT-cabling | CablePro | 机房多走一趟桥架 | 机房北侧新增一段桥架以承接新增网络端口路径；与 GC 开孔配合。 | ¥22,000.00 |  | No schedule impact | 技术确认 | 2026-08-20T11:00:00+08:00 | 2026-08-21T15:00:00+08:00 | 2026-08-25T09:00:00+08:00 | 2026-08-25T09:00:00+08:00 | 2026-08-28T18:00:00+08:00 |  |  |  |  | 01_IT-cabling_CablePro/04_变更洽商/ | 商务尚未启动