## Invoice
PAYMENT NO: 2
Project: | Apple SARL Phase 5 Build Out Project
Division: | 212-4
Vendor: | Schneider Electric (China) Co., Ltd.
Work Package: | BMS
Vendor Reference Number: | SE-BMS-2026-02
PO Number : | PO-F26651-BMS
PO Value: | 1000000 | (CNY exclude 9% VAT)
Contract Value: | 1000000 | (CNY exclude 9% VAT)
Vendor: | Schneider Electric (China) Co., Ltd. |  |  |  |  | Office Address:
Contact Point: | Wang Lei |  |  |  |  | 北京市朝阳区示例路 1 号
Contact Number: | 13900001111
Office: | 010-88886666
Division: | [8 empty] | Payment Claim No.
212 | Apple R&D (Beijing) Limited | [7 empty] | 2
1. 预付款 / Advance 10% 2. 到货 / Delivery 30% 3. 验收 / Acceptance 60% | [7 empty] | Period
1
Contract Value |  |  |  | RMB | 1000000
Add: Variations to-date |  |  |  | RMB | 0
Adjusted Contract Value |  |  |  | RMB
到货 / Delivery | [8 empty] | 300000
Total Invoice Value | [8 empty] | 300000
LESS payment previously certified | [8 empty] | 100000
TOTAL CLAIM | [8 empty] | 200000
PAYMENT APPROVALS
Date
Signature |  |  | Date |  |  |  | Project Manager
Notes:
Please note the following assumptions
(a) This invoice without VAT
(b) Please see attached email for approval.
Note on B2: 填SC2即可
Note on B3: 填Div 166/183/etc
Note on B4: 供应商名字
Note on B5: GC
Note on B6: 供应商编号 (PO上可找到）
Note on B7: PO 编号
Note on B8: PO 金额
Note on B9: 合同总价
Note on B11: 供应商联系人信息
Note on K12: 供应商公司地址
Note on B19: 苹果公司 div 166 或183 名字全称 (PO 上可找到）
Note on B22: 付款节点
Note on P23: 周期
Note on I29: 合同总价
Note on B37: 请款节点
Note on Q37: 请款金额
Note on Q41: 已付款金额，如初次申请则为0

## Advance Payment Schedule (hidden)
AMOUNT
1) | ADVANCE PAYMENT AS PER ADVACE PAYMENT CERTIFICATE NO. 1 - Feb 2014 (TBC) | [5 empty] | 12000000000
3) | LESS : ADVANCE PAYMENT PAYBACK TO DATE
|  | Payback | Included in | Certificate | Payback Amount
|  | Payment No | Certificate No | Date
|  | No 1 | No 2 | 2014-04-01
|  | No 2 | No 3 | 2014-05-01
|  | No 3 | No 4 | 2014-06-01 | 1701600000
|  | No 4 | No 5 | 2014-07-01 | 2297100000
|  | No 5 | No 6 | 2014-08-01 | 639700000
|  | No 6 | No 7 | 2014-09-14 | 598000000 |  |  | -3534800000
|  | No 7 | No 8
|  | No 8 | No 9
|  | No 9 | No 10
|  | No 10 | No 11 + 12
|  | No 11 | No 13
|  | No 12 | No 14
|  | No 13 | No 15
|  | No 14 | No 16
|  | No 15 | No 17
|  | No 16 | No 18
|  | No 17 | No 19
|  | No 18 | No 20
|  | No 19 | No 21
|  | No 20 | No 22
|  | No 21 | No 23
|  | No 22 | No 24
|  | No 23 | No 25
|  | No 24 |  |  | 0
No 25
[5 empty] | ADVANCE PAYMENT BALANCE | R
8465200000